## Development Plan
Development Plan
:Add your fundraising philosphy statement here:
GOALS |  |  | CAMPAIGN STRATEGY | DATES/TIMELINE | LED BY | RESPONSIBLE PARTY | STATUS & NOTES | REVENUE BUDGET | TO-DATE | REMAINING | EXPENSE BUDGET | TO-DATE | ESTIMATED COST PER DOLLAR
Individual/Annual Giving - PURPOSE STATEMENT ex. Foster and encourage engagement through individual financial support.
|  | ex. Major Gifts | Develop and identify prospects for major giving using past data and outside information | Jan/Feb for prospecting and March/April for outreach | Development Volunteer 1 | Board Chair | March - We have developed a list of 27 individuals who have consistently given in the past who we believe have more capacity to give. We will create an outreach calendar and plan to start later this month. | 10000 | 0 | 10000 | NA | NA | $.08 from the literature
ex. Recurring Gifts
ex. Annual Giving
ex. Board Giving
Corporate & Foundation - PURPOSE STATEMENT ex. Establish, foster and diversify investment by corporations and foundations.
|  | ex. Foundation Support | Effectively research and do outreach to foundations in advance of grant applications. Come up with a calendar with a mangeable number of grants per year. | Jan for prospecting. Follow grants calendar | Development Volunteer 2 | Staff Member 1 | March - We have developed a list off 9 grants that are spaced throughout the year that have funded other similar organizations. We have had initial conversations with 4 of the 9. The first grant application is due in May | 15000 | 0 | 15000 | NA | NA | $.20 from the literature
ex Corporate Support
Special Events - PURPOSE STATEMENT ex. Foster engagement, community and income with strategic special events
ex. Gala
|  | ex. Garden Parties | Work with Board members to put on 3 Garden Parties throughout the year. They will invite their contacts. The goal is $1500 per party | One party in February, two in the summer | Board members X,Y and Z | Board Chair | March - we had a greenhouse party hosted at the arboretum in February. 17 people attended and we made $1800. Committees are forming for the summer parties. | 4500 | 1800 | 2700 | 1500 | 875 | $.50 from the literature
Government - PURPOSE STATEMENT ex. Maintain and grow relationships with Government and Arts Councils
ex. Local Grants
ex. Statwide Grants
ex. Federal Grants
Marketing/Comms - PURPOSE STATEMENT ex. Be more intentional in the synergies and collaboration between development and communications.
ex. Development Committe Collaboration
ex. Shared Calendar
Planned Giving- PURPOSE STATEMENT ex. Have a clear and advertised program for planned and estate giving.
ex. Planned giving
Stewardship- PURPOSE STATEMENT ex. Cultivate our donor base by increased communication and gratitude
ex. Donor outreach and stewardship
ex. Data
Earned Income- PURPOSE STATEMENT ex. aintain strong ticket sales and other earned income streams and increase revenue where possible
ex. Ticketing
ex. Paid Performances
ex. Program ads and Merchandise
ex. Membership Dues
Culture of Philantropy- PURPOSE STATEMENT ex. Invest in internal stakeholder engagement in philantropy and provide information and tools
ex. Board Development
ex. Membership Development
Development Operations- PURPOSE STATEMENT ex. create a culture and framework to support development and fundraising work
ex. CRM utilization
ex. Regular meetings